## Sheet1
No | Description | Doer | Start Date | End Date | Deadline
1 | Design page sign in by Angular | Trang | 2018-05-07 | 2018-05-07 | 2018-05-08
2 | Design page sign up by Angular | Công | 2018-05-07 | 2018-05-07 | 2018-05-08
3 | Integrate JWT into Spring Boot | Trí | 2018-05-07 | 2018-05-07
4 | Build api to save new account & design add new account page | Công | 2018-05-08 |  | 2018-05-09
5 | Design page view list account & detail account | Hạnh | 2018-05-08 |  | 2018-05-09
6 | Build api to update and delete account | Trang | 2018-05-08 |  | 2018-05-09
7 | Sign up with google, facebook. Validate data input | Trí | 2018-05-08